## Closeout checklist
CONSTRUCTION CLOSEOUT CHECKLIST
Work it from the top before the final invoice. Mark a row Done only when the evidence is in the job file.
Project |  |  |  | Done
Checked on |  |  |  | Outstanding
Not applicable
Section | Item | Evidence | Responsible | Status | Date | Where filed | Notes
Permits and inspections | Every permit closed, with the final inspection record | Inspection record from the permit holder
Permits and inspections | Your own test and inspection records filed | Flood or pressure tests, QC checklist sign-offs
Permits and inspections | Start-up or commissioning records for installed equipment | Installer's start-up sheet
Changes and money | Every change order signed and billed | Signed change orders, invoice references
Changes and money | Allowances reconciled against what was bought | Purchase orders and supplier bills
Changes and money | Supplier and subcontractor bills received and matched to purchase orders | Bills, PO log
Changes and money | Final invoice issued, with holdback or retainage shown as retained | Final invoice
Warranties and manuals | Contractor's workmanship warranty, in writing | Warranty letter
Warranties and manuals | Manufacturer manuals and warranties collected | PDFs and paper copies
Warranties and manuals | Warranty start date recorded for each | Handover register
Records | Products, colours and lot numbers recorded | Handover register
Records | Photos of concealed work kept with the job | Dated job photos
Records | Changes from the drawings marked up | Marked-up drawings
Outstanding items | Deficiency list signed, or every open item dated and assigned | Deficiency list
Handover | Owner walk-through: shut-offs, controls, care and maintenance | Daily log entry
Handover | Keys, codes, remotes and spare materials handed over | Handover register
Handover | Site protection removed and the site left clean
Not on this checklist, on purpose
Substantial performance or completion | A legal milestone set by your contract and your province's or state's legislation, often certified by the owner's consultant. A finished checklist does not establish it.
Holdback or retainage release | Released when the contract and the legislation allow, usually after a period with no lien registered. The checklist records that holdback was shown as retained, not that it is due.
The lien period | Starts from a date the legislation defines, which may not be the day you hand over the keys. Check the rule where the job is.
Not legal advice. Confirm each against your contract and the legislation where the job is.

## Handover register
HANDOVER REGISTER
Everything handed to the owner, with the date and an acknowledgement. Keep a copy in the job file.
Given |  | Still to give
Document or item | What it covers | Format / where | Version or date | Given to | Date given | Acknowledged

## Example - checklist
CONSTRUCTION CLOSEOUT CHECKLIST - WORKED EXAMPLE
EXAMPLE ONLY - the fictional ensuite job used across our templates, at handover.
Project | Example: ensuite renovation, Edmonton AB (fictional) |  |  | Done
Checked on | 2027-05-31 |  |  | Outstanding
Not applicable
Section | Item | Evidence | Responsible | Status | Date | Where filed | Notes
Permits and inspections | Permit closed, if one was taken out | Final inspection record from the permit holder | Client (permit by owner, per the scope) | Outstanding |  |  | Ask for a copy for the job file. Do not mark it done on a verbal
Permits and inspections | Shower waterproofing flood test | QC checklist sign-off, photo 2027-03-25-flood-test-24h.jpg | D. Kaur, site lead | Done | 2027-03-25 | Job documents: Inspection
Permits and inspections | Every tap, drain and flush run and checked for leaks | Final walk note in the daily log | Plumbing sub | Done | 2027-05-28 | Daily log
Permits and inspections | Electrical permit |  |  | Not applicable |  |  | Electrical work is excluded from the scope
Changes and money | Every change order signed and billed | CO-001 signed 2027-03-22; billed on INV-1003 | Contractor | Done | 2027-05-31 | Job documents: Change order
Changes and money | Fixture allowance reconciled against what was bought | PO-203, inside the $2,800 allowance | Contractor | Done | 2027-05-31 | Purchase orders
Changes and money | Final invoice issued, with holdback shown as retained | INV-1003 | Contractor | Done | 2027-05-31 | Invoices | Holdback release is not on this checklist: see the note below
Warranties and manuals | Contractor's workmanship warranty, in writing | Warranty letter, on the terms in your contract | Contractor | Done | 2027-05-31 | Job documents: Warranty
Warranties and manuals | Manufacturer manuals and warranties: vanity, toilet, faucets, glass door | PDFs and the paper copies | Fixture and glass suppliers | Outstanding |  | Job documents: Warranty | Glass door care and warranty sheet not yet received from the supplier
Records | Tile, grout and membrane product names and lot numbers recorded | Handover register | Contractor | Done | 2027-05-31 | Handover register | So a repair years later matches
Records | Photos of the open walls and substrate kept with the job | 2027-03-15-shower-open-to-studs.jpg, 2027-03-15-bottom-plate-dry.jpg | D. Kaur, site lead | Done | 2027-03-15 | Job photos
Records | Paint colours and sheens recorded | Handover register | Contractor | Done | 2027-05-31 | Handover register
Outstanding items | Deficiency list signed, or every open item dated and assigned | Deficiency list from the final walk | Contractor | Outstanding |  |  | Glass door sweep to adjust, due 4 Jun 2027
Handover | Spare materials left with the owner | One box of tile and a part bag of grout | Contractor | Done | 2027-05-31 | Handover register
Handover | Owner walk-through: shut-off valves, grout and glass care | Daily log entry | D. Kaur, site lead | Done | 2027-05-28 | Daily log
Handover | Site protection removed, lockbox returned |  | D. Kaur, site lead | Done | 2027-05-31
Not on this checklist, on purpose
Substantial performance or completion | A legal milestone set by your contract and your province's or state's legislation, often certified by the owner's consultant. A finished checklist does not establish it.
Holdback or retainage release | Released when the contract and the legislation allow, usually after a period with no lien registered. The checklist records that holdback was shown as retained, not that it is due.
The lien period | Starts from a date the legislation defines, which may not be the day you hand over the keys. Check the rule where the job is.
Not legal advice. Confirm each against your contract and the legislation where the job is.

## Example - register
HANDOVER REGISTER - WORKED EXAMPLE
Everything handed to the owner, with the date and an acknowledgement. Keep a copy in the job file.
Given |  | Still to give
Document or item | What it covers | Format / where | Version or date | Given to | Date given | Acknowledged
Workmanship warranty letter | The contractor's warranty on the ensuite work | PDF and paper | 2027-05-31 | Client | 2027-05-31 | Initialled
Fixture manuals and warranties | Vanity, toilet and faucets | Paper in the vanity drawer, PDF | As supplied | Client | 2027-05-31 | Initialled
Glass door care and warranty sheet | Frameless shower door (CO-001)
Product record | Tile, grout, membrane and paint: product, colour and lot number | PDF | 2027-05-31 | Client | 2027-05-31 | Initialled
Waterproofing record | Flood test sign-off and the photos before tile | PDF | 2027-03-25 | Client | 2027-05-31 | Initialled
Change order and final invoice | CO-001 and INV-1003 | PDF | 2027-05-31 | Client | 2027-05-31 | Initialled
Spare materials | One box of tile, part bag of grout | On the garage shelf |  | Client | 2027-05-31 | Initialled