## Cost codes
CONSTRUCTION COST CODES
One row per cost code. Budget comes from the estimate lines coded to it; committed from open POs; billed from approved bills. Labour logged on the job is not in this sheet (see the job costing template).
Cost code | Category | Phase | Budget (cost) | Committed (unbilled POs) | Billed | Remaining before labour
100 | Site prep & demolition
200 | Foundation & concrete
300 | Framing & structure
400 | Roofing & exterior
500 | Windows & doors
600 | Plumbing
700 | Electrical
800 | HVAC
900 | Insulation & drywall
1000 | Finishes & painting
1100 | Flooring & tile
1200 | Fixtures & appliances
1300 | Landscaping
1400 | Permits & fees
1500 | Contingency
TOTALS
Codes and categories are BuildersBridge's own residential list, not a licensed classification standard. Rename, renumber or add rows to match your books.
Template by BuildersBridge (buildersbridge.ca). Free to use and edit.

## Example - estimate to bill
CONSTRUCTION COST CODES - WORKED EXAMPLE
One row per cost code. Budget comes from the estimate lines coded to it; committed from open POs; billed from approved bills. Labour logged on the job is not in this sheet (see the job costing template).
Cost code | Category | Phase | Budget (cost) | Committed (unbilled POs) | Billed | Remaining before labour
100 | Site prep & demolition | Demolition
600 | Plumbing | Rough-in
1000 | Finishes & painting | Finishes
1100 | Flooring & tile | Finishes
1200 | Fixtures & appliances | Fixtures and trim
TOTALS
Estimate lines, each with its cost code
Line | Cost code | Qty | Unit | Unit cost | Cost
Demolition and disposal | 100 | 16 | h | 75
Tile installation, shower and floor | 1100 | 52 | sq ft | 18
Plumbing fixture swap (licensed sub) | 600 | 1 | lot | 2400
Paint walls and ceiling | 1000 | 10 | h | 65
Porcelain tile, 52 sq ft + waste | 1100 | 58 | sq ft | 9.5
Membrane, setting materials, grout | 1100 | 1 | lot | 420
Vanity, toilet and fixtures (allowance) | 1200 | 1 | allowance | 2800
Disposal bin | 100 | 1 | ea | 450
Purchase orders
PO | Vendor | Cost code | PO total | Status | Billed |  | Committed
PO-201 | Tile supplier (fictional) | 1100 | 971 | Received | 971
PO-202 | Plumbing sub (fictional) | 600 | 2400 | Sent | 1200
PO-203 | Fixture supplier (fictional) | 1200 | 2800 | Sent | 0
PO-204 | Glass supplier (fictional) | 1200 | 1000 | Draft | 0
Approved bills
Vendor | Cost code | Against PO | Amount
Tile supplier (fictional) | 1100 | PO-201 | 971
Plumbing sub (fictional) | 600 | PO-202 | 1200
Disposal bin (fictional) | 100 | No PO | 450
Codes and categories are BuildersBridge's own residential list, not a licensed classification standard. Rename, renumber or add rows to match your books.
Template by BuildersBridge (buildersbridge.ca). Free to use and edit.