## Punch list
Item ID | Location / room | Issue description | Responsible trade / person | Priority | Date raised | Due date | Status | Photo / reference | Completion date | Verified by | Sign-off date | Notes | Overdue?
Summary
Items logged
Still open
Verified / closed
Overdue
Overdue ignores rows with no due date, rows already completed, and rows already closed.

## Filled example
EXAMPLE ONLY - illustrative data, not a real project. Delete this sheet or work in 'Punch list'.
Item ID | Location / room | Issue description | Responsible trade / person | Priority | Date raised | Due date | Status | Photo / reference | Completion date | Verified by | Sign-off date | Notes | Overdue?
PL-001 | Kitchen | Cabinet door misaligned, rubs frame on close | Millwork - T. Okafor | Medium | 2026-08-10 | 2026-08-20 | Verified - closed | photos/kitchen-cab-01.jpg | 2026-08-18 | Site super - A. Reid | 2026-08-19 | Adjusted hinge, re-checked on walkthrough
PL-002 | Ensuite | Grout haze on shower floor tile | Tile - Bolt Trades | Low | 2026-08-10 | 2026-08-24 | Ready to verify | photos/ensuite-floor.jpg | 2026-08-22 |  |  | Cleaned; needs verifying at final walk
PL-003 | Main floor hall | Drywall corner bead dented beside light switch | Drywall - Sparks Ltd | Medium | 2026-08-11 | 2026-08-21 | Open | photos/hall-corner.jpg |  |  |  | Trade notified 11 Aug
PL-004 | Garage | Exterior door does not latch without lifting | Carpentry - in house | High | 2026-08-12 | 2026-08-18 | In progress | photos/garage-door.jpg |  |  |  | Strike plate on order
PL-005 | Rear deck | Two deck boards cupping at the north end | Carpentry - in house | Medium | 2026-08-14 |  | Open | photos/deck-north.jpg |  |  |  | Monitoring through first season - no due date set
PL-006 | Basement | Paint touch-up at stair stringer | Painting - Pacific Finish | Low | 2026-08-15 | 2026-09-30 | Open |  |  |  |  | Scheduled with final paint pass
PL-007 | Front entry | Client asked about a storm door - not in contract | n/a | Low | 2026-08-16 |  | Not applicable |  |  |  |  | Out of scope; logged so it is not raised again
Formulas:
Overdue? = IF(OR([Due date]="",[Completion date]<>"",[Status]="Verified - closed",[Status]="Not applicable"),"",IF([Due date]<TODAY(),"Overdue",""))

## How to use
Construction punch list / deficiency list
1. Walk the job and log every item as you find it. One row per item, one location per row.
2. Name a responsible trade or person. An item with nobody against it does not get fixed.
3. Set a due date. Leave it blank only where there genuinely is not one - the overdue
column ignores blank due dates rather than flagging them, and it stops flagging a row
as soon as the completion date is filled, so a job waiting on your verification is not
held against the trade.
4. When the trade says it is done, set status to 'Ready to verify' and fill the completion date.
5. Verify it yourself on a later walk, then fill 'Verified by' and the sign-off date and set
status to 'Verified - closed'. Completion and verification are separate columns on purpose:
the trade saying it is fixed and you confirming it are two different facts.
'Deficiency list' and 'punch list' mean the same document. Deficiency list is the more common
term on Canadian residential contracts; punch list is the American usage.
This is a working document, not a legal one. Closing every row here does not by itself
establish substantial completion, occupancy or a holdback release - those are set by your
contract and your province's legislation.