## RFI form (blank)
Request for information
Blank form. One question per RFI.
Project name
Project number
RFI number
Raised by
Sent to
Date issued
Response required by
Drawing / specification reference
Status
Question
Proposed interpretation (optional)
Attachments
Potential cost / schedule impact
Response
Answered by
Date answered
An answer to an RFI is not by itself approval of extra cost or time. If the response changes the scope, raise a change order under your contract.

## RFI form (example)
Request for information
EXAMPLE ONLY - illustrative, not a real project.
Project name | Henderson Residence - basement development
Project number | NB-2038
RFI number | RFI-004
Raised by | A. Reid, site supervisor
Sent to | M. Chen, project architect
Date issued | 2026-08-18
Response required by | 2026-08-22
Drawing / specification reference | A-203 rev C, detail 4; spec section 06 10 00
Status | Answered
Question | Drawing A-203 rev C shows the beam pocket at grid C/2 bearing on the existing foundation wall, but the wall is 190mm block, not the 240mm shown. What bearing detail should be used?
Proposed interpretation (optional) | Proposed: pour a 400 x 400 x 200mm concrete pad on the block, doweled into the wall, and bear the beam on that. Please confirm or issue an alternative detail.
Attachments | Photo of existing wall at grid C/2; marked-up A-203
Potential cost / schedule impact | Schedule: framing at grid C on hold, about 2 days. Cost: not yet priced - a pad pour is a small extra if the detail is accepted.
Response | Use the pad as proposed, 400 x 400 x 200mm, 20 MPa, two 15M dowels epoxied 150mm into the block. Revised detail issued as A-203 rev D.
Answered by | M. Chen, architect
Date answered | 2026-08-21
An answer to an RFI is not by itself approval of extra cost or time. If the response changes the scope, raise a change order under your contract.

## Tracking log
RFI number | Subject | Raised by | Sent to | Date issued | Response due | Date answered | Status | Drawing / spec reference | Follow-up required | Days open
RFI-001 | Window head height, front elevation | A. Reid | M. Chen | 2026-07-28 | 2026-08-01 | 2026-07-31 | Answered | A-101 rev B | No
RFI-002 | Kitchen island outlet locations | A. Reid | Owner | 2026-08-04 | 2026-08-08 | 2026-08-11 | Answered | E-201 rev A | No
RFI-003 | Stair headroom at basement landing | T. Okafor | M. Chen | 2026-08-12 | 2026-08-15 |  | Open | A-301 rev A | Yes - chase before framing
RFI-004 | Beam bearing at grid C/2 | A. Reid | M. Chen | 2026-08-18 | 2026-08-22 | 2026-08-21 | Answered | A-203 rev C | No - rev D issued
Summary
RFIs raised
Answered
Still open
Formulas:
Days open = IF([Date issued]="","",IF([Date answered]="",TODAY()-[Date issued],[Date answered]-[Date issued]))

## How to use
Construction RFI form and tracking log
1. One question per RFI. An RFI asking three things gets one answer and two gaps.
2. Always cite the drawing or specification and its revision. 'The plans show' is not a
reference anyone can check a year later.
3. Say what you think the answer is. A proposed interpretation turns a question the
designer has to solve into one they only have to confirm, which is usually faster.
4. State the impact if you know it - what is on hold and roughly for how long.
5. Copy the RFI number into the tracking log the day you send it, not the day it comes back.
6. The log's 'Days open' counts to the answer date, or to today while it is still open.
RFI, submittal and change order are three different documents. An RFI asks what was
intended. A submittal proposes a product or method for approval. A change order records
an agreed change to price or time. An RFI answer can lead to a change order; it is not one.
This is a standalone template. BuildersBridge does not currently include an RFI or
submittal workflow - use this alongside it, and store the completed forms with the job.