## Scope of work
SCOPE OF WORK
Describes the work so both sides agree what is in and out. It is not a contract: use it with your contract, reviewed for your province or state.
Project
Client
Contractor
Date
Estimate reference
INCLUDED WORK
1
2
3
4
5
6
7
8
EXCLUSIONS
1
2
3
4
5
ASSUMPTIONS
1
2
3
4
5
RESPONSIBILITIES
Item | Who | When
ALLOWANCES
Item | Amount (before tax)
MILESTONES AND ACCEPTANCE
Milestone | Acceptance criteria | Accepted by | Date
SIGN-OFF
Client signature and date
Contractor signature and date
Template by BuildersBridge (buildersbridge.ca). Free to use and edit. Not legal advice.

## Example - fictional job
SCOPE OF WORK - WORKED EXAMPLE
Describes the work so both sides agree what is in and out. It is not a contract: use it with your contract, reviewed for your province or state.
Project | Example: ensuite renovation, Edmonton AB (fictional)
Client | Example client (fictional)
Contractor | Example contractor (fictional)
Date | 2027-03-01
Estimate reference | EST-1042
INCLUDED WORK
1 | Remove existing shower tile, floor tile, vanity and toilet; dispose of debris off site.
2 | Install waterproof membrane in the shower; tile shower walls and floor and the bathroom floor (52 sq ft).
3 | Supply and install vanity, toilet and fixtures within the $2,800 allowance.
4 | Licensed plumber to disconnect and reconnect fixtures; no relocation of drains or supply lines.
5 | Patch and paint walls and ceiling, two coats.
6
7
8
EXCLUSIONS
1 | Repairs to framing, subfloor or plumbing found behind finishes; priced as a change order.
2 | Fixtures above the allowance; the difference is priced as a change order.
3 | Permit fees (permit by owner), electrical work, and heating or ventilation changes.
4
5
ASSUMPTIONS
1 | Existing drain and supply locations stay where they are.
2 | The room is empty and accessible on weekdays from 8:00 to 17:00.
3 | Tile selection confirmed before demolition starts.
4
5
RESPONSIBILITIES
Item | Who | When
Tile and fixture selections | Client | Before start
Permit | Client | Before start
Plumbing disconnect and reconnect | Plumbing sub | Rough-in and finish
Site protection and daily clean-up | Contractor | Throughout
ALLOWANCES
Item | Amount (before tax)
Vanity, toilet and fixtures | 2800
MILESTONES AND ACCEPTANCE
Milestone | Acceptance criteria | Accepted by | Date
Demolition complete | Walls and floor open to inspection; client walk-through
Waterproofing and tile complete | Membrane flood test passed; tile grouted and sealed
Fixtures set and painted | All fixtures working; final walk-through and deficiency list signed
SIGN-OFF
Client signature and date
Contractor signature and date
Template by BuildersBridge (buildersbridge.ca). Free to use and edit. Not legal advice.