## Submittal log
CONSTRUCTION SUBMITTAL LOG
One row per revision. A resubmission is a new row with the next revision number, so the history stays visible.
Project |  |  |  |  | Closed
Project number |  |  |  |  | With reviewer
Overdue with reviewer
Back with you to resubmit
Not sent - past its submit-by date
Submittal no. | Rev | Spec section | Item | Type | Submitted by | Reviewer | Date sent | Review days allowed | Return due | Date returned | Disposition | Lead time (weeks) | Needed on site | Submit by | Projected on site | Status | Days late on site (projected) | Notes
Formulas:
Projected on site = IF([Date sent]="","",IF([Date returned]<>"",[Date returned],MAX([Return due],TODAY()))+N([Lead time (weeks)])*7)

## Example - basement job
CONSTRUCTION SUBMITTAL LOG - WORKED EXAMPLE
EXAMPLE ONLY - a fictional basement job, the same one as the RFI template example.
Project | Henderson Residence - basement development (fictional) |  |  |  | Closed
Project number | NB-2038 |  |  |  | With reviewer
Overdue with reviewer
Back with you to resubmit
Not sent - past its submit-by date
Submittal no. | Rev | Spec section | Item | Type | Submitted by | Reviewer | Date sent | Review days allowed | Return due | Date returned | Disposition | Lead time (weeks) | Needed on site | Submit by | Projected on site | Status | Days late on site (projected) | Notes
SUB-001 | 0 | 07 21 00 Thermal insulation | Basement wall insulation and vapour barrier | Product data | Insulation sub | M. Chen, architect | 2026-07-30 | 7 |  | 2026-08-05 | Reviewed - no exceptions | 1 | 2026-09-08
SUB-002 | 0 | 06 43 00 Wood stairs and railings | Basement stair: stringers, treads and guard | Shop drawing | Stair fabricator | M. Chen, architect | 2026-08-06 | 10 |  | 2026-08-14 | Revise and resubmit | 4 | 2026-09-21 |  |  |  |  | Headroom at the landing below the minimum shown on A-301. Raised as RFI-003
SUB-002 | 1 | 06 43 00 Wood stairs and railings | Basement stair: stringers, treads and guard | Shop drawing | Stair fabricator | M. Chen, architect | 2026-08-17 | 10 |  |  |  | 4 | 2026-09-21 |  |  |  |  | Reviewer holding it until RFI-003 is answered
SUB-003 | 0 | 06 17 13 Laminated veneer lumber | LVL beam at grid C/2 and its bearing pad | Product data | Framing - in house | M. Chen, architect | 2026-08-21 | 5 |  | 2026-08-25 | Reviewed as noted | 1 | 2026-09-01 |  |  |  |  | Bear on the pad detailed in A-203 rev D (answer to RFI-004)
SUB-004 | 0 | 08 14 16 Flush wood doors | Interior doors and hardware | Product data | Finish carpentry | Owner |  | 7 |  |  |  | 6 | 2026-10-05 |  |  |  |  | Owner still choosing hardware
SUB-005 | 0 | 09 65 19 Resilient tile flooring | Basement vinyl plank flooring | Sample | Flooring sub | Owner | 2026-08-20 | 7 |  | 2026-08-24 | Reviewed - no exceptions | 2 | 2026-10-13
Formulas:
Projected on site = IF([Date sent]="","",IF([Date returned]<>"",[Date returned],MAX([Return due],TODAY()))+N([Lead time (weeks)])*7)

## How to use
Construction submittal log
1. List what the specification asks you to submit before you buy or build it: shop drawings, product data,
samples, mock-ups, test reports. One item per submittal number.
2. Fill 'Needed on site', the lead time in weeks and the review days your contract allows. 'Submit by'
works backwards from them: needed on site, less the lead time, less the review period.
3. Log the date you send it. 'Return due' and 'Projected on site' follow, and Status reads 'Overdue with
reviewer' once the review period has passed without an answer.
4. When it comes back, enter the date and the disposition exactly as the reviewer's stamp gives it.
5. If it comes back 'Revise and resubmit', add a new row with the same number and the next revision.
The earlier row reads 'Superseded', so the history stays and the count does not double.
6. 'Days late on site' compares the projected delivery with the date you need it. A resubmission that
eats the review float shows up here weeks before the material is missing.
A submittal proposes something for review. An RFI asks a question. A shop drawing is one kind of
submittal. A reviewed stamp checks conformance with the design intent; it does not usually take over
responsibility for dimensions, quantities or means and methods. Read the stamp and your contract.
Status and projected dates use TODAY(), so they change as you work the log. The example was read on
2026-08-29.